## Overall Plan
No | Date | To Do | Detail Discription | Timeline | Person Responsible | Used budgets
1 | 2022-08-01 | Rent Car | rent "Myint Express Bus" for 2 days; 15000 per person and total 3 buses | 9sept 5:30PM to 10:30PM and 11sept 6:00PM to 11PM | (peter) manager of Myint Express Bus, (John & Jean)Secretaries leader, Admin Team leader & (holly) finance department | 30 lakhs
2 | 2022-08-01 | Hotel Booking | rent "Hill Garden Hotel " for 3(40000=one room, one room=3 persons, 1 person= 14000);including breakfast & total 35 rooms | 9sept 11PM (Check in) 11sept 6PM (check out) | (sofia) hotel reception, (John & Jean)Secretaries leader and Admin Team leader and (holly) finance department | 15 lakhs
3 | 2022-08-20 | Motivision Speaker | Ei Mon Soe (for Public Speaker and Trainer) | 10sept 10:15AM to 12:15PM 11sept 1:15AM to 3:15PM | (John & Jean)Secretaries leader and Admin Team leader | 10 lakhs
4 | 2022-08-20 | Doctor for health care and health for the trip | Dr. Aung Kyaw Wynn ( for health care meeting and health care for employees) | 10sept 1:30PM to 3:30PM 11sept 1:30PM to 3:30PM | (John & Jean)Secretaries leader and Admin Team leader | 20 lakhs
5 | 2022-08-15 | Meeting Room | rent "Hill Garden Hotel " for meeting room | 10sept 8AM to 5:30PM 11sept 8AM to 5:30PM | (Linda) hotel manager, (John & Jean)Secretaries leader and Admin Team leader and (holly) finance department | 20 lakhs
6 | 2022-08-10 | Ordering Shirt | Order Shirt with Logo of the Company at "Blue Summer Clothing" | 10Spet and 11 Sept (8AM to 5:30PM) | (Sarah) Clothing company employee, (Jean)Admin Team leader and (holly) finance department | 5 lakhs
7 | 2022-08-25 | Bike Rental | Bike Rental at the beach | 10 sept 6PM to 7PM | (Micheal)Bike rental shop employee, (Dr. Aung Kyaw Wynn)For health care, (Jean)Admin Team leader and (holly) finance department | 2 lakhs
8 | 2022-08-01 | Lunch + Dinner | Buffet Lunch and Dinner from hotel (Order the Lunch and Dinner hours to Hotel) | 9sept 12AM to 1AM, 10sept 12:15PM to 1:15PM, 7PM to 8PM;11sept 12:15PM to 1:15PM | (Billie) hotel admin, (Cal) Hotel cook, (John & Jean)Secretaries leader and Admin Team leader and (holly) finance department | 20 lakhs
9 | 2022-09-02 | Snacks | Snacks for car and during meeting Hours snacks | 9sept , 10sept , 11sept | (Billie) hotel admin, (Oliva) Hotel employee, (John) Admin Team leader | 5 lakhs
10 | 2022-09-01 | Shoppping | Buy Nessary Things and Medicine | 1PM to 4PM | (John) Admin Team leader, (holly) finance department, (Wanda) Stuff department | 3 lakhs
11 | 2022-08-01 | Backup Plan | Any nessary backup product or emergacy can be used | 9sept, 10sept, 11sept | (Dr. Aung Kyaw Wynn)For health care, (Jean)Admin Team leader and (carmilla)Hr department | 20 lakhs
Total= 150 Buget
Invitation
No | Date | To Do | Detail Discription | Timeline | Person Responsible | Used budgets
1 | 2022-08-01 | Announce the employee | Tell them the plans and responsibility about the trip and personal uses | 9AM to 11:00AM | (John & Jean)Secretaries leader and Admin Team leader, (carmilla)Hr department, (holly) finance department | No buget used
2 | 2022-08-09 | Send invitation to the doctor | Invite him to attend the health care meeting and tell him stand by doctor for accidents and hotel plans | 9AM to 10:00AM | (John & Jean)Secretaries leader and Admin Team leader | No buget used
4 | 2022-08-10 | Send invitation to the motivision speaker | Invite her to attend the meeting and tell her hotel plans | 9AM to 10:00AM | (John & Jean)Secretaries leader and Admin Team leader | No buget used
5 | 2022-08-10 | Send invitation to the motivision speaker | Invite her to attend the meeting and tell her hotel plans | 9AM to 10:00AM | (John & Jean)Secretaries leader and Admin Team leader | No buget used

## Day2
Date | No | To Do | Detail Discription | Timeline | Person responsible | used budget
Meeting Plans
2022-09-11 | 1 | Meeting 1 | Customer Services meeting | 8AM to 10AM | Customer servies dapartment employees | Already Paid
[7 empty] | Activty Details | Requiremnts | Reward
2022-09-11 | 2 | Meeting 2 | Team working meeting | 10:15AM to 12:15PM | IT department employee | No need | One of the group leaders will be shouting "Red Light, Green Light" by facing the sea and suddenly they will turn around by shouting "Red Light" and 9 group leaders from each group will be at the end of the beach with that leader and watching all the employee who move during red light. All the employee must run from start of the beach to the end where the leader is standing and run beyond the line without getting out of the games by stooping at red light and running at green light when leader is facing the sea. | None | Free Lunch during 1 working day
2022-09-11 | 2 | During Meeting 2 | Picky Boo Activity | 11AM to 11:30PM | Group leaders | Already Paid
2022-09-11 | 3 | Meeting 3 | Ei Mon Soe (for Public Speaker and Trainer) | 1:30AM to 3:30PM | Ei Mon Soe (for Public Speaker and Trainer) | Already Paid | Activty Details | Requiremnts | Reward
2022-09-11 | 3 | During Meeting 3 | Bingo Activity | 2PM to 2:30PM | Ei Mon Soe (for Public Speaker and Trainer) and every group leaders | Already Paid | 10 people in 1 group, 10 group in total, 2 papers per group fills with random numbers and while group members are helping the person who is circling the paper by numbers leader will be shouting out randomly and win the game as a group by circling up all the numbers in the paper and shout "BINGO". | Bells (as hotel check in bells) and pens and paper [Already paied as shopping fee] | Free Lunch during 1 working day
2022-09-11 | 4 | Meeting 4 | Dr. Aung Kyaw Wynn ( for health care meeting ) | 3:30PM to 5:30PM | Dr. Aung Kyaw Wynn(doctor, health care) | Already Paid
Employees Personal Time Activities
2022-09-10 | 5 | Game Activity | Swimming Race | 6:30 AM to 7:30AM | (Dr. Aung Kyaw Wynn)For health care, (Jean)Admin Team leader | No need
Meals
2022-09-11 | 6 | Breakfast | Buffet Breakfast and breakfast only avalible within breakfast hour | 7AM to 8AM | (Linda) hotel manager, (Billie) hotel admin, (Cal) Hotel cook, Hotel Employees & Hotel Waiters | Already Paid
2022-09-11 | 7 | Breaktime | employee go for a walk or smoke or eat snacks and chill | 15min (10AM to 10:15AM) | No need | Already Paid
2022-09-11 | 8 | Lunch | Lunch only avalible within lunch hours (Buffet) | 12:15PM to 1:15PM | (Linda) hotel manager, (Billie) hotel admin, (Cal) Hotel cook, Hotel Employees & Hotel Waiters | Already Paid
2022-09-11 | 9 | Breaktime | employee go for a walk or smoke or eat snacks and chill | 15min (3:15AM to 3:30AM) | No need | Already Paid
2022-09-11 | 10 | Leave | The bus will leave at 6PM | 6PM to 12:30AM | No need | Already Paid
Total= 150 Buget

## Day1
Date | No | To Do | Detail Discription | Timeline | Person responsible | used budget
Meeting Plans
2022-09-10 | 1 | Meeting 1 | Dr. Aung Kyaw Wynn ( for health care meeting ) | 8AM to 10AM | Dr. Aung Kyaw Wynn(doctor, health care) | Already Paid
[7 empty] | Activty Details | Requiremnts | Reward
2022-09-10 | 2 | Meeting 2 | Ei Mon Soe (for Public Speaker and Trainer) | 10:15AM to 12:15PM | Ei Mon Soe (for Public Speaker and Trainer) | Already Paid | 10 people in 1 group, 10 group in total and leader of all group will ask 30 fun and random questions and the fast group who tell the answer get the 10 points pre questions and get 100 points to win the game. | Bells (as hotel check in bells) and pens and paper [Already paid as shopping fee] | Free 1 hour rest within work hours during 1 working day
2022-09-10 | 2 | During Meeting 2 | Trivia Night Activity | 11AM to 11:30PM | Ei Mon Soe (for Public Speaker and Trainer) and every group leaders | Already Paid
2022-09-10 | 3 | Meeting 3 | Team working meeting | 1:15AM to 3:15PM | IT department employee | No need | Activty Details | Requiremnts | Reward
2022-09-10 | 3 | During Meeting 3 | Sand Castle Activity | 2PM to 2:30PM | Group leaders | Already Paid | 10 people in 1 group, 10 groups in total and group members will discuss how they going to build the sand castle and the best builder in the group will build within 30 minutes and the best castle team win. | Shovals and buckets. | Free 1 hour rest within work hours during 1 working day
2022-09-10 | 4 | Meeting 4 | Customer Services meeting | 3:30PM to 5:30PM | Customer servies dapartment employees | No need
Meals
2022-09-10 | 5 | Dinner | Dinner only avalible within Dinner hours (Buffet), Rules= No drinking alcohol, be back to hotel rooom at 1AM maximium; | 12AM to 1AM | Linda) hotel manager, (Billie) hotel admin, (Cal) Hotel cook, Hotel Employees & Hotel Waiters | Already Paid
2022-09-10 | 6 | Breakfast | Buffet Breakfast and breakfast only avalible within breakfast hour | 7AM to 8AM | Linda) hotel manager, (Billie) hotel admin, (Cal) Hotel cook, Hotel Employees & Hotel Waiters | Already Paid
2022-09-10 | 7 | Breaktime | employee go for a walk or smoke or eat snacks and chill | 15min (10AM to 10:15AM) | No need | Already Paid
2022-09-10 | 8 | Lunch | Lunch only avalible within lunch hours (Buffet) | 12:15PM to 1:15PM | Linda) hotel manager, (Billie) hotel admin, (Cal) Hotel cook, Hotel Employees & Hotel Waiters | Already Paid
2022-09-10 | 9 | Breaktime | employee go for a walk or smoke or eat snacks and chill | 15min (3:15AM to 3:30AM) | No need | Already Paid
2022-09-10 | 10 | Dinner | Dinner only avalible within Dinner hours (Buffet), Rules= No drinking alcohol, be back to hotel rooom at 10PM maximium; | 7PM to 8PM | Linda) hotel manager, (Billie) hotel admin, (Cal) Hotel cook, Hotel Employees & Hotel Waiters | Already Paid
Employees Personal Time Activities
2022-09-10 | 11 | Game Activity | Bike race(10miles) | 6PM to 7PM | (Micheal)Bike rental shop employee, (Dr. Aung Kyaw Wynn)For health care, (Jean)Admin Team leader | Already Paid
2022-09-10 | 12 | Rest | Personal Time | Starts 8PM | No need | No need
2022-09-11 | 13 | Arrival | The bus will arrival at 12AM | 5:30PM to 12AM | No need | Already Paid
Total= 150 Buget